## excel (6)
/Non Project/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Project Settings
Project Owner | Fredy Benavides Gordillo
Start Date | mar 20, 2017 05:04:10 PM
Completion Date | mar 21, 2017 12:23:34 PM |  |  |  | Completed: *
Keywords
Language | Java
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 41.7 | 69 | 40.3
Planned Time | 0.14375 |  | 0.60625
Actual Tiempo |  | 0.15764 | 0.66944
CPI (Cost-Performance Index) |  |  | 0.91
% Reuse | 0% | 0% | 2.11%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 2.58 | 0 | 1.54
Total Defects/KLOC or equivalent | 36.2 | 19.2 | 29.3
Yield % | 57.1% | 80% | 63.2%
Code Review Rate | 1280 | 626 | 793
Program Size
| Plan | Actual | A la Fecha
Base (B) | 0 | 0 | 0
Deleted (D) | 0 | 0 | 0
Modified (M) | 0 | 0 | 0
Added (A) | 144 | 261 | 648
Reused (R) | 0 | 0 | 14
Added and Modified (A+M) | 144 | 261 | 648
Total Size (T) | 144 | 261 | 662
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 106 | 261 | 652
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.017361 | 0.013889 | 0.075694 | 11.3%
DiseÃ±o | 0.016667 | 0.011806 | 0.070833 | 10.6%
RevisiÃ³n de DiseÃ±o | 0.0034722 | 0.0048611 | 0.015972 | 2.39%
CodificaciÃ³n | 0.080556 | 0.085417 | 0.37083 | 55.4%
RevisiÃ³n de CodificaciÃ³n | 0.0048611 | 0.017361 | 0.034028 | 5.08%
CompilaciÃ³n | 0.0097222 | 0.00625 | 0.039583 | 5.91%
Pruebas | 0.0069444 | 0.0090278 | 0.032639 | 4.88%
Postmortem | 0.0055556 | 0.0090278 | 0.029861 | 4.46%
Total | 0.14375 | 0.15764 | 0.66944
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0 | 0%
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 2.23 | 2 | 8 | 42.1%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 2.98 | 3 | 11 | 57.9%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0 | 0 | 0 | 0%
Total | 5.21 | 5 | 19
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0 | 0 | 0 | 0%
RevisiÃ³n de DiseÃ±o | 0.74 | 2 | 4 | 21.1%
CodificaciÃ³n | 1.86 | 0 | 5 | 26.3%
RevisiÃ³n de CodificaciÃ³n | 0.37 | 2 | 3 | 15.8%
CompilaciÃ³n | 1.86 | 1 | 6 | 31.6%
Pruebas | 0.37 | 0 | 1 | 5.26%
Total | 5.21 | 5 | 19
After Development | 0 | 0 | 0
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 9.92 | 17.1 | 10.4
Defects/Hour - Code Review | 3.31 | 4.8 | 3.67
Defects/Hour - Compile | 8.27 | 6.67 | 6.32
Defects/Hour - Test | 2.33 | 0 | 1.28
DRL (DLDR/UT) | 4.25 | 13.4 | 8.17
DRL (Code Review/UT) | 1.42 | 3.76 | 2.88
DRL (Compile/UT) | 3.54 | 5.22 | 4.95
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 12:47 PM el 21/03/2017